## Sheet1
TASK | DATE TO FINISH | DATE FINISHED | DIFF
1. Login / Register screen. | 2026-03-23 | 2026-04-01 | 9
2. Home screen (your leagues overview) | 2026-03-24 | 2026-04-01 | 8
3. Create or join a league screen | 2026-03-25 |  | -46106
4. League dashboard (standings, points table) | 2026-03-26 |  | -46107
5. Squad screen (your drivers, main driver selector) | 2026-03-27 |  | -46108
6. Transfer market screen (buy/steal drivers, raise clause) | 2026-03-28 |  | -46109
7. Weekly prediction screen (rank top 10 drivers before Thursday) | 2026-03-29 |  | -46110
8. Season prediction screen (top 10 drivers & constructors) | 2026-03-30 |  | -46111
9. Profile screen (change password, profile picture, delete account) | 2026-03-31 |  | -46112
10. Admin panel (user overview, create/edit/delete users) | 2026-04-01 |  | -46113
Formulas:
DATE TO FINISH = [DATE TO FINISH, row above]+1